## How to use
Agency client onboarding checklist
Template by Jasper — heyjasper.ai
How to use
1. Type the client and the kickoff date at the top of the Checklist sheet. Due dates follow from the kickoff date.
2. Put an owner against each step and change "Days from kickoff" to suit how you work. Negative numbers are days before kickoff.
3. Delete steps you never do, or mark them Not needed for this client. There are 20 spare rows at the bottom for your own steps.
4. Update the status as you go. Late steps that are not done turn red.
5. Access: ask the client to invite your team as users. Where a password cannot be avoided, share it through a password manager, never by email or chat.
Yellow cells are for you to fill in. Grey cells work things out: leave them alone.
Opens in Excel, Google Sheets (File > Import) and LibreOffice.
Onboarding a client every month? Keep your onboarding process in the Jasper wiki, with every version saved: heyjasper.ai/product/wiki-intranet
Free to use and change in your own business. Please don't resell this file or publish it as your own.

## Checklist
Client onboarding checklist
Client
Kickoff date
Done so far
Stage | Step | Owner | Days from kickoff | Due | Status | Notes | Stage | Done | Steps | % done
Internal handoff | Sales hands over the signed proposal, the scope and anything promised to the client |  | -5 |  | Not started |  | Internal handoff
Internal handoff | Name the account lead and the delivery team |  | -5 |  | Not started |  | Scope and billing
Internal handoff | Set up the client and project in your time tracking and project tools |  | -3 |  | Not started |  | Stakeholders
Internal handoff | Start an internal notes page for the client |  | -3 |  | Not started |  | Access (by invite only)
Scope and billing | Confirm the signed scope or statement of work |  | -3 |  | Not started |  | Kickoff
Scope and billing | Agree what is out of scope and how change requests work |  | -3 |  | Not started |  | First month
Scope and billing | Confirm who approves work and who approves invoices on the client side |  | -2 |  | Not started
Scope and billing | Get the billing contact, any purchase order number and invoicing rules |  | -2 |  | Not started
Scope and billing | Send the deposit or first invoice, if your terms include one |  | -2 |  | Not started
Scope and billing | Set up the budget or retainer, and how unused hours are handled |  | 0 |  | Not started
Stakeholders | List the client's people: name, role, email, and what each one decides |  | -2 |  | Not started
Stakeholders | Send the onboarding questionnaire: goals, audience, competitors, brand, past work |  | -2 |  | Not started
Stakeholders | Review the answers as a team before kickoff |  | -1 |  | Not started
Access (by invite only) | Domain and DNS: ask for your own user on the registrar or DNS host, or have the client make changes |  | 0 |  | Not started
Access (by invite only) | Hosting and the website's admin: one named account per person, not a shared login |  | 0 |  | Not started
Access (by invite only) | Analytics and Search Console: ask the client to add your team as users |  | 0 |  | Not started
Access (by invite only) | Ad accounts: request access through the platform's own access settings |  | 0 |  | Not started
Access (by invite only) | Social accounts: ask for access through the platform's partner or role settings |  | 0 |  | Not started
Access (by invite only) | Brand assets: logos, fonts, guidelines and photos in one shared folder |  | 0 |  | Not started
Access (by invite only) | Anything that has to be a password: share it through a password manager, never by email or chat |  | 0 |  | Not started
Access (by invite only) | Record who has access to what, so it can be removed when the work ends |  | 0 |  | Not started
Kickoff | Send the agenda before the meeting |  | -2 |  | Not started
Kickoff | Introductions: who does what on both sides |  | 0 |  | Not started
Kickoff | Goals, and how you will measure success |  | 0 |  | Not started
Kickoff | Scope, timeline and first milestones |  | 0 |  | Not started
Kickoff | How you will keep in touch, how often, and how fast you reply |  | 0 |  | Not started
Kickoff | How approvals and feedback rounds work |  | 0 |  | Not started
Kickoff | Reporting: what, how often, and who receives it |  | 0 |  | Not started
Kickoff | Send notes, decisions and next steps |  | 1 |  | Not started
First month | Send the first status update |  | 7 |  | Not started
First month | Deliver the first piece of work |  | 14 |  | Not started
First month | Internal review: hours against budget, scope changes and risks |  | 28 |  | Not started
First month | 30-day review with the client: what is working and what to change |  | 30 |  | Not started