## How to use
New employee onboarding checklist
Template by Jasper — heyjasper.ai
How to use
1. Type the new starter's name and first day at the top of the Checklist sheet. Due dates follow from the first day.
2. Each step has a suggested owner. Change the owners and "Days from the first day" to suit your team. Negative numbers are days before the first day.
3. Delete steps you never do, or mark them Not needed for this person. There are 20 spare rows at the bottom for your own steps.
4. Update the status as you go. Late steps that are not done turn red.
5. Employment paperwork depends on your country and state: follow the official guide for where the person works.
6. Client access: new staff get their own logins to client tools, never a shared password. Where a password cannot be avoided, share it through a password manager, never by email or chat.
Yellow cells are for you to fill in. Grey cells work things out: leave them alone.
Opens in Excel, Google Sheets (File > Import) and LibreOffice.
Running onboarding training by hand? Jasper Learn assigns courses with rules that keep new starters enrolled: heyjasper.ai/product/lms
Free to use and change in your own business. Please don't resell this file or publish it as your own.

## Checklist
New employee onboarding checklist
New starter
First day
Done so far
Stage | Step | Owner | Days from the first day | Due | Status | Notes | Stage | Done | Steps | % done
Before day one | Send a welcome email: start time, where to go or how to log in, and who they will meet | Manager | -5 |  | Not started |  | Before day one
Before day one | Choose a buddy who isn't their manager | Manager | -5 |  | Not started |  | Day one
Before day one | Order or set up their laptop and anything else they need | IT or office | -5 |  | Not started |  | First week
Before day one | Employment paperwork: contract, tax and pay details, and any checks the law requires where you are (see the official guides) | Manager | -3 |  | Not started |  | First month
Before day one | Create their accounts: email, chat, calendar, time tracking and project tools | IT or office | -3 |  | Not started
Before day one | Add them to the right teams, channels and client projects | Manager | -2 |  | Not started
Before day one | Book their first-week meetings: one-to-ones, a team intro and buddy catch-ups | Manager | -2 |  | Not started
Day one | Welcome and introductions to the team | Manager | 0 |  | Not started
Day one | Laptop, logins and two-factor authentication set up | IT or office | 0 |  | Not started
Day one | Password manager set up, and how we share client passwords (never by email or chat) | IT or office | 0 |  | Not started
Day one | Walk through the handbook or intranet: policies, leave, expenses and who to ask | Manager | 0 |  | Not started
Day one | Workplace safety basics: emergency procedures, or a home-office check for remote staff | Manager | 0 |  | Not started
Day one | Lunch or a coffee with their buddy | Buddy | 0 |  | Not started
First week | How we track time: clients, projects, billable or not, and when timesheets are due | Manager | 1 |  | Not started
First week | Log a full day of time and check it together | New starter | 1 |  | Not started
First week | How we work with clients: who talks to them, how requests come in and how approvals work | Manager | 1 |  | Not started
First week | Client access by invite: request their own logins to client tools, never shared ones | New starter | 2 |  | Not started
First week | Sit in on a client call or a project meeting | Buddy | 2 |  | Not started
First week | Meet the people they will work with most | Buddy | 2 |  | Not started
First week | Start the training courses assigned to new starters | New starter | 2 |  | Not started
First week | A small first piece of real work | Manager | 3 |  | Not started
First week | End-of-week check-in: questions, what to change, and goals for the first month | Manager | 4 |  | Not started
First month | Agree goals for the first 30, 60 and 90 days | Manager | 7 |  | Not started
First month | 30-day check-in with their manager | Manager | 30 |  | Not started
First month | Ask for feedback on onboarding and update this checklist | Manager | 30 |  | Not started